## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  | Completed | STQ = Single Table Queries
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
STQ (lines 11 - 162) | 7 | 5 | 7 | 4 | 100% | bar: PERIODS 8
STQ (lines 162 - 375) | 7 | 5 | 7 | 3 | 100%
STQ (lines 376 - 499) | 7 | 5 | 8 | 3 | 100%
STQ (lines 500 - 625) | 7 | 5 | 9 | 2 | 100%
STQ (lines 626 - 750) | 7 | 5 | 9 | 3 | 100%
STQ (exercise) 1 + 2 + 4 | 1 | 11 | 2 | 2 | 100%
STQ (exercise) 3 + 5 | 1 | 11 | 3 | 2 | 100%
STQ (exercise) 6 | 1 | 11 | 4 | 1 | 100%
STQ (exercise) 7 + 8 | 1 | 11 | 3 | 3 | 100%
STQ (exercise) 9 + 10 | 1 | 11 | 3 | 2 | 100%
Member 1 video | 2 | 10 | 10 | 1 | 100%
Member 2 video | 2 | 10 | 10 | 1 | 100%
Member 3 video | 2 | 10 | 10 | 1 | 100%
Member 4 video | 2 | 10 | 9 | 1 | 100%
Member 5 video | 2 | 10 | 9 | 1 | 100%