## Group member 1
To-do list
To be completed by: |  | 2024-02-07 |  | Name: Damian Rozpedowski
Deadline: |  | 2024-02-07 |  | Date: 2/3/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-03 | 2024-02-03 | 2/4/2024 | 1 | Set up development enviroment.
100% | Preparation | 2024-02-03 | 2024-02-03 | 2/4/2025 | 1 | Verify SQL queries on TSQLV4 DB
100% | Task 1 | 2024-02-04 | 2024-02-05 | 2/5/2026 | 1 | Modify TSQLV4 query for Northwinds
100% | Task 2 | 2024-02-04 | 2024-02-05 | 2/5/2027 | 1 | Modify TSQLV4 query for Northwinds
100% | Task 4 | 2024-02-04 | 2024-02-05 | 2/5/2028 | 1 | Modify TSQLV4 query for Northwinds
100% | Paperwork | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2 | Create SQL Jupyter Notebook
100% | Hand-off | 2024-02-06 | 2024-02-07 | N/A | 1 | Notebook, MP4
0% | Follow-up | 2024-02-06 | 2024-02-07 | N/A | N/A | N/A

## Group member 2
To-do list
To be completed by: |  | 2024-02-07 |  | Name: Hasnatul Hosna
Deadline: |  | 2024-02-07 |  | Date: 2/3/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-03 | 2024-02-03 | 2/4/2024 | 1 | Set up development enviroment.
100% | Preparation | 2024-02-03 | 2024-02-03 | 2/4/2025 | 1 | Verify SQL queries on TSQLV4 DB
100% | Task 3 | 2024-02-04 | 2024-02-05 | 2/5/2026 | 1 | Modify TSQLV4 query for Northwinds
100% | Task 5 | 2024-02-04 | 2024-02-05 | 2/5/2027 | 1 | Modify TSQLV4 query for Northwinds
100% | Paperwork | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2 | Create SQL Jupyter Notebook
100% | Hand-off | 2024-02-06 | 2024-02-07 | N/A | 1 | Notebook, MP4
0% | Follow-up | 2024-02-06 | 2024-02-07 | N/A | N/A | N/A

## Group member 3
To-do list
To be completed by: |  | 2024-02-07 |  | Name: Hannah Kurian
Deadline: |  | 2024-02-07 |  | Date: 2/3/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-03 | 2024-02-03 | 2/4/2024 | 1 | Set up development enviroment.
100% | Preparation | 2024-02-03 | 2024-02-03 | 2/4/2025 | 1 | Verify SQL queries on TSQLV4 DB
100% | Task 7 | 2024-02-04 | 2024-02-05 | 2/5/2026 | 1 | Modify TSQLV4 query for Northwinds
100% | Task 8 | 2024-02-04 | 2024-02-05 | 2/5/2027 | 1 | Modify TSQLV4 query for Northwinds
100% | Paperwork | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2 | Create SQL Jupyter Notebook
100% | Hand-off | 2024-02-06 | 2024-02-07 | N/A | 1 | Notebook, MP4
0% | Follow-up | 2024-02-06 | 2024-02-07 | N/A | N/A | N/A

## Group member 4
To-do list
To be completed by: |  | 2024-02-07 |  | Name: Essmer Sanchez
Deadline: |  | 2024-02-07 |  | Date: 2/3/24
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-03 | 2024-02-03 | 2/4/2024 | 1 | Set up development enviroment.
100% | Preparation | 2024-02-03 | 2024-02-03 | 2/4/2025 | 1 | Verify SQL queries on TSQLV4 DB
100% | Task 9 | 2024-02-04 | 2024-02-05 | 2/5/2026 | 1 | Modify TSQLV4 query for Northwinds
100% | Task 10 | 2024-02-04 | 2024-02-05 | 2/5/2027 | 1 | Modify TSQLV4 query for Northwinds
100% | Paperwork | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2 | Create SQL Jupyter Notebook
100% | Hand-off | 2024-02-06 | 2024-02-07 | N/A | 1 | Notebook, MP4
0% | Follow-up | 2024-02-06 | 2024-02-07 | N/A | N/A | N/A

## Group member 5
To-do list
To be completed by: |  | 2024-02-07 |  | Name: Zicheng Yang
Deadline: |  | 2024-02-07 |  | Date: 2/3/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-03 | 2024-02-03 | 2/4/2024 | 1 | Set up development enviroment.
100% | Preparation | 2024-02-03 | 2024-02-03 | 2/4/2025 | 1 | Verify SQL queries on TSQLV4 DB
100% | Task 6 | 2024-02-04 | 2024-02-05 | 2/5/2029 | 1 | Modify TSQLV4 query for Northwinds
100% | Paperwork | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2 | Create SQL Jupyter Notebook
100% | Hand-off | 2024-02-06 | 2024-02-07 | N/A | 1 | Notebook, MP4
0% | Follow-up | 2024-02-06 | 2024-02-07 | N/A | N/A | N/A

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up